## FI - ROAD CONSTRUCTION
FRONTENAC ISLANDS ROAD CONSTRUCTION SCHEDULE
WI - WOLFE ISLAND HI - HOWE ISLAND
Road | KM's | Projected Start | Projected Completion
|  | Date | Date
CONSTRUCTION
North Shore Rd (HI) | 4.1 | Mid August | End of August
Howe Island Dr. to St. Philomena's Church | 6.2 | Mid August | End of August
RE-SURFACING
Marysville Streets (WI)
Hillcrest St | 0.16 | 2023-07-12 | 2023-07-14
Allen St | 0.1 | 2023-07-12 | 2023-07-14
Thunder Rd | 0.07 | 2023-07-12 | 2023-07-14
Eliza St | 0.3 | 2023-07-12 | 2023-07-14
Center St | 0.11 | 2023-07-12 | 2023-07-14
Leander St | 0.14 | 2023-07-12 | 2023-07-14
St Lawrence St | 0.17 | 2023-07-12 | 2023-07-14
Cross St | 0.23 | 2023-07-12 | 2023-07-14
Barrett St | 0.16 | 2023-07-12 | 2023-07-14
Lucinda St | 0.18 | 2023-07-12 | 2023-07-14
Going St | 0.22 | 2023-07-12 | 2023-07-14
Reeds Bay Rd (WI) | 1.6 | 2023-07-11 | 2023-07-14
9th Line (Baseline to end) (WI) | 4.3 | 2023-07-11 | 2023-07-14
Pulverizing
Baseline to Hickey Point (HI) | 1.3 | Mid August | End of August
Spithead Rd (HI) | 1.1 | Mid August | End of August
Baseline Rd (Between 8th and 9th) (WI) | 1.36 | 2023-07-12 | 2023-07-14
Carpenter's Point Rd - East End (WI) | 0.7 | 2023-07-12 | 2023-07-14
TOTAL | 22.5
Note on A12: Dianne: